## Guam ops
|  |  |  | Guam Operations and Flight Schedule | [30 empty] | Guam Operations Center Staffing: 21 June 2010
[6 empty] | Active flight status | [8 empty] | Non flight status or unknown status
Name | Affiliation | check in | check out | August | [21 empty] | September | [29 empty] | October
 | time axis 2010-08-10 to 2010-10-20
Pete Black | NRL | 2010-08-12 | 2010-10-22 | bar: 2010-08-12 to 2010-10-20
Mike Ohmart | UW-APL | 2010-08-12 | 2010-10-22 | bar: 2010-08-12 to 2010-10-20
Jeff Kerling | NAVO | 2010-08-18 | 2010-09-18 | bar: 2010-08-18 to 2010-09-18
Tony DePalma | NPS | 2010-08-18 | 2010-09-18 | bar: 2010-08-18 to 2010-09-18
Jeff Hawkins | NRL | 2010-08-18 | 2010-09-03 | bar: 2010-08-18 to 2010-09-03
Andy Penny | NPS | 2010-09-01 | 2010-09-18 | bar: 2010-09-01 to 2010-09-18
Bob Creasey | NPS | 2010-10-04 | 2010-10-22 | bar: 2010-10-04 to 2010-10-20
Heather Hornick | NPS | 2010-09-14 | 2010-10-22 | bar: 2010-09-14 to 2010-10-20
Daniel Jacob | UM | 2010-08-18 | 2010-09-18 | bar: 2010-08-18 to 2010-09-18
JTWC TDO 1 | JTWC | 2010-08-18 | 2010-09-03 | 2010-08-18: TD1; 2010-08-19: TD1; 2010-08-20: TD1; 2010-08-21: TD1; 2010-08-22: TD1; 2010-08-23: TD1; 2010-08-24: TD1; 2010-08-25: TD1; 2010-08-26: TD1; 2010-08-27: TD1; 2010-08-28: TD1; 2010-08-29: TD1; 2010-08-30: TD1; 2010-08-31: TD1; 2010-09-01: TD1; 2010-09-02: TD1; 2010-09-03: TD1
JTWC TDO 2 | JTWC | 2010-09-01 | 2010-09-17 | 2010-09-01: TD2; 2010-09-02: TD2; 2010-09-03: TD2; 2010-09-04: TD2; 2010-09-05: TD2; 2010-09-06: TD2; 2010-09-07: TD2; 2010-09-08: TD2; 2010-09-09: TD2; 2010-09-10: TD2; 2010-09-11: TD2; 2010-09-12: TD2; 2010-09-13: TD2; 2010-09-14: TD2; 2010-09-15: TD2; 2010-09-16: TD2; 2010-09-17: TD2
JTWC TDO 3 | JTWC | 2010-09-15 | 2010-10-01 | 2010-09-15: TD3; 2010-09-16: TD3; 2010-09-17: TD3; 2010-09-18: TD3; 2010-09-19: TD3; 2010-09-20: TD3; 2010-09-21: TD3; 2010-09-22: TD3; 2010-09-23: TD3; 2010-09-24: TD3; 2010-09-25: TD3; 2010-09-26: TD3; 2010-09-27: TD3; 2010-09-28: TD3; 2010-09-29: TD3; 2010-09-30: TD3; 2010-10-01: TD3
JTWC TDO 4 | JTWC | 2010-09-29 | 2010-10-15 | 2010-09-29: TD4; 2010-09-30: TD4; 2010-10-01: TD4; 2010-10-02: TD4; 2010-10-03: TD4; 2010-10-04: TD4; 2010-10-05: TD4; 2010-10-06: TD4; 2010-10-07: TD4; 2010-10-08: TD4; 2010-10-09: TD4; 2010-10-10: TD4; 2010-10-11: TD4; 2010-10-12: TD4; 2010-10-13: TD4; 2010-10-14: TD4; 2010-10-15: TD4
CDR Matt Moore | JTWC/NMFC | 2010-09-19 | 2010-10-10 | bar: 2010-09-19 to 2010-10-10
CDR Dan Eleuterio | ONR | 2010-09-19 | 2010-10-01 | bar: 2010-09-19 to 2010-10-01
CDR Chuck Bragg | SPAWAR | 2010-09-29 | 2010-10-22 | bar: 2010-09-29 to 2010-10-20
Chris McCall | UCSD | 2010-08-18 | 2010-10-22 | bar: 2010-08-18 to 2010-10-20

## Sheet2
[5 empty] | Monterey Operations Schedule | [30 empty] | Monterey Operations Center Staffing: 21 June 2010
[7 empty] | Science Support | [8 empty] | Science Support: Part Time - Sometime during the period will be in MRY
Name | U.S. | Affiliation | check in | check out | August | [21 empty] | September | [29 empty] | October
 | time axis 2010-08-10 to 2010-10-20
Eric D'Asaro | x | APL/UW | 2010-08-15 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20
Jim Price | x | WHOI | 2010-08-18 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20
YaTing Chang |  | NTU | 2010-08-18 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20
Rosalinda Fortier | x | APL/UW | 2010-08-18 | 2010-09-28 | bar: 2010-08-18 to 2010-09-28
Brandon Kearns | x | UM | 2010-09-26 | 2010-10-21 | bar: 2010-09-26 to 2010-10-20
Shuyi Chen | x | UM | 2010-08-18 | 2010-08-21 | bar: 2010-08-18 to 2010-08-21
Craig Lee | x | APL/UW | 2010-08-18 | 2010-10-21 | bar: 2010-08-18 to 2010-10-20
Luca Centurioni |  | UCSD | 2010-08-18 | 2010-10-21 | bar: 2010-08-18 to 2010-10-20
Jerome Patoux |  | APL/UW | 2010-08-17 | 2010-08-24 | bar: 2010-08-17 to 2010-08-24
Chia-Rong Chen |  | CWB | 2010-09-01 | 2010-09-14 | 2010-09-01: CRC; 2010-09-02: CRC; 2010-09-03: CRC; 2010-09-04: CRC; 2010-09-05: CRC; 2010-09-06: CRC; 2010-09-07: CRC; 2010-09-08: CRC; 2010-09-09: CRC; 2010-09-10: CRC; 2010-09-11: CRC; 2010-09-12: CRC; 2010-09-13: CRC; 2010-09-14: CRC
Ralph Foster | x | APL/UW | bar: 2010-08-18 to 2010-10-20
Dariusz Baranowski |  | UCSD | 2010-08-17 | 2010-09-17 | bar: 2010-08-17 to 2010-09-17
I.I. Lin |  | NTU | 2010-09-01 | 2010-09-14 | bar: 2010-09-01 to 2010-09-14
Visiting Forecaster Support
Grant Elliott |  | BoM | 2010-08-10 | 2010-09-25 | bar: 2010-08-10 to 2010-09-25
Gary Foley |  | BoM | 2010-09-20 | 2010-10-21 | bar: 2010-09-20 to 2010-10-20
Local Science Support
Pat Harr |  | NPS | 2010-08-15 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20
Russ Elsberry |  | NPS | 2010-08-15 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20
Bob Creasey |  | NPS | 2010-08-15 | 2010-10-01 | bar: 2010-08-15 to 2010-10-01
Andy Penny |  | NPS | 2010-08-15 | 2010-08-28 | bar: 2010-08-15 to 2010-08-28
|  |  | 2010-09-25 | 2010-10-21 | bar: 2010-09-25 to 2010-10-20
Tony DePalma | bar: 2010-09-25 to 2010-10-20
Heather Hornick | bar: 2010-08-15 to 2010-09-10
Mary Jordan |  | NPS | 2010-08-15 | 2010-10-21 | bar: 2010-08-15 to 2010-10-20