NOMADSS Project Charter

Title: Nitrogen, Oxidants, Mercury and Aerosol Distributions, Sources & Sinks

P.I./Institution: Alex Guenther / NCAR; Daniel Jaffe / U Washington; Xianliang Zhou / Wadsworth Center and School of Public Health

Project Location: Smyrna, TN

Project Period:  1 June – 15 July 2013

Facilities requested: NSF/NCAR C-130, TOGA, HARP, FO3

- Project Summary:

  - Scope:

The purpose of the NOMADSS project is to conduct low altitude airborne trace gas sampling over south eastern and east coastal regions of the United States.  The scope includes preparation for the field campaign, actual field work, data collection, follow-up data processing, data archival, and project closure activities.  Specific tasks are as follows:

- An integrated NOMADSS payload on the C-130 at Rocky Mountain Municipal Airport (RMMA) by the last week of May 2013.

- Successful completion of up to eight hours of test flights at the end of the payload integration period before aircraft departure to Tennessee.

- Conduct of 150 research flight hours on the C-130 during the NOMADSS field campaign from 1 June – 15 July 2013.

- Support of an EOL Data Center from 1 June – 15 July 2013.

- Provision of field-processed quick-look data within 24 hours following completion of flight.

- Release of a processed and quality-controlled RAF core data set in netCDF format three months after the completion of the NOMADSS field campaign.

  - Science:

NOMADSS is the result of a merger of three complimentary field campaigns: SOAS, NAAMEX, and TROPHONO.  The study goals include a regional survey of photo-chemical constituents in rural southern eastern United States (SOAS), an examination of major mercury sources and the mapping of mercury distributions and transformations in the eastern United States (NAAMEX),  and to establish HONO distributions and the mechanics of its production in various continental and maritime air masses (TROPHONO).

  - Roles and Responsibilities

Specific EOL staff have been assigned to support NOMADSS.  Direct requests for services should pass through either the Project Lead or the Aircraft Lead for coordination of effort.

| Position | Name | Email Address |
| --- | --- | --- |
| Project Lead | Vidal Salazar | vidal@ucar.edu |
| Aircraft Lead | Allen Schanot | schanot@ucar.edu |
| Lead Pilot | Edward Ringleman | ringlema@ucar.edu |
| Safety Officer | TBD |  |
| IT Support | Mike Paxson | mpaxson@ucar.edu |
| Data Services | TBD |  |
| Shipping | Randy Klotz | klotz@ucar.edu |

- Resources:

This project needs the following resources to perform the tasks described in this document.

  - Platform / Payload

The NSF/NCAR C-130 will be equipped with in-situ and remote sensing instrumentation, including the HAIS TOGA, AWAS, GT-CIMS, T of F-AMS and HARP Actinic Flux sensors as well as a number of ACD and User supplied systems (see table below).  A total of 88 flight hours on the NSF/NCAR C-130 have been requested, of which 80 are research flight hours and are test flight hours .

| Instrument | Lead | Location |
| --- | --- | --- |
| RAF Mission Scientist Display | Webster | flight deck |
| RAF State Parameters | Schanot | fuselage |
| RAF Fast Hygrometer | Beaton | fuselage |
| RAF Fast Temperature | Schanot | fuselage |
| RAF SPP-100 Cloud Probe | Rogers | right wing pod |
| RAF SPP-300 Aerosol Probe | Jensen | right wing pod |
| RAF PCASP Aerosol Probe | Rogers | left wing pod |
| RAF UHSAS Aerosol Probe | Rogers | left wing pod |
| RAF King Probe Liquid Water | Schanot | right wing |
| RAF Cloud Base Temperature | Schanot | fuselage |
| RAF Radiometric Surface Temperature | Schanot | fuselage |
| RAF Up/Down IR Irradiance | Haggerty | fuselage |
| RAF Up/Down SW Irradiance | Haggerty | fuselage |
| RAF CN Counter | Schanot | fuselage / SMAI 1 |
| RAF Digital Imagery: Fwd & Down | Beaton | fuselage |
| EOL HARP - Up/Down Actinic Flux | Hall | fuselage |
| CARI NO-NOX | Weinheimer | cabin / HIMIL (1) inlet |
| CARI / HAIS Fast Ozone | Campos | cabin / HIMIL (1) inlet |
| CARI Carbon Monoxide | Campos | cabin / HIMIL (1) inlet |
| CARI Picarro Carbon Dioxide | Flocke | cabin / HIMIL (1) inlet |
| ACD SMPS Aerosol System | Smith / Ortega | cabin / SMAI 2 |
| SOAS Specific Systems |  |  |
| EOL / HAIS TOGA | Apel | cabin / HIMIL (3) inlet |
| NCAR / ACD PTRMS | Karl | cabin / inlet |
| NAAMEX Specific Systems |  |  |
| UW GEM Mercury | Jaffe | cabin /Special inlet (A) |
| UW GOM Mercury | Jaffe | cabin /Special inlet (A) |
| UW GOM / PHG | Jaffe | cabin /Special inlet (A) |
| CU HOx / H2SO4 | Maulden / Cantrell | cabin / Special inlet (B) |
| TROPHONO Specific Systems |  |  |
| SUNY HONO / HNO3 | Zhou | cabin / HIMIL (4) inlet |
| SUNY pNO3 / pOrganics | Zhou | cabin / SDI inlet |
| SUNY Bulk Aerosol | Zhou | cabin / SDI inlet |
| UCLA Mini - DOAS | Stutz | CAI aperture pad |

  - Deliverables / Services

    - FPS Project Services

    - Data center

A common area will be provided at the local hotel housing project staff that will be equipped with internet access and a LAN for data distribution.  Space for individual groups will be provided with full time SA support for IT activities and the room will serve as the real time command and control center for C-130 research flights.

    - Field Data Catalog

CDS will prepare and support a standard Field Data Catalog for the project.  Aircraft track plots will be initialized for both the C-130 and NOAA P-3 aircraft.  Special funds are required for this support.

    - Data Archive

CDS will prepare and support standard data archival services for the NOMADSS project.  The archive is to include C-130 netCDF data files from all C-130 flights along with coincident data from all onboard sensors supported by other participants.  Potential access to NOAA P-3 data and from the SOAS ground site will be handled as a separate request.  Special funds are required for this support.

    - Communications

Real time air-to-ground communications will be provided by EOL via internet XCHAT and RT data feed with AEROS display capability.  Project coordination will be conducted via email and cell phone links along with key information postings at the Data Center.

    - Logistics

EOL will coordinate the preparation of and provide transport for User support equipment traveling from Rocky Mountain Municipal Airport to the deployment location in Smyrna, TN.  Seatainers will be used as shipping containers and will serve as secure storage near the C-130 in Smyrna.

    - DFS services

The design and fabrication of all new infrastructure required to mount User systems on the C-130 for NOMADSS will be provided by EOL staff and the costs will be covered by the project deployment pool allocation.  User supplied specialty inlets and provisions for heating sample tubing are excluded from this allocation.

  - Staffing

Earth Observing Laboratory Staffing:

# 2 RAF Pilots

- 1 RAF Mechanics

- 2 RAF Flight Engineers

# 4 RAF Technicians

- 1 RAF Project Manager

- 1 RAF Instrumentation Scientist

- 1 CDS System Administrator

- 1 RAF Software Engineer

- 1 FPS Program Director

- 1 CDS Data Catalog  Administrator

Atmospheric Chemistry Division/CARI Staffing:

# 6 ACD Research Associates

To support fast-response ozone, carbon dioxide, oxides of nitrogen, HARP actinic flux, SMPS aerosol sizing, TOGA and carbon monoxide, five staff from the ACD division will be required to support NOMADSS.  Field support of the instruments requires funding for four special hires for a total of fourteen weeks, which was included in the C-130 cost estimate.

- Scheduling:

  - Milestone Schedule

The Project Manager will obtain approval from the Project Sponsor for any schedule changes which impact the project completion milestone.

| Date | Milestone Description | Deliverable |
| --- | --- | --- |
| 28 December 2012 | Finalize FBO arrangements | Contract for space |
| 28 December 2012 | Finalize group housing | Group rate room allocation |
| 1 February 2013 | Finalize payload | User Documentation |
| 1 April 2013 | Start payload integration |  |
| 18 June 2013 | Payload integration completed |  |
| 27 June 2013 | Test flights completed |  |
| 28 June 2013 | C-130 prepped for departure |  |
| 28 June 2013 | Seatainer shipment departs BJC |  |
| 30 June 2013 | C-130 departure for Smyrna |  |
| 1 June 2013 | Start of NOMADSS |  |
| 15 July 2013 | End of NOMADSS |  |
| 17 July 2013 | C-130 arrival in CO |  |
| 26 July 2013 | Payload de-install completed |  |
| 14 August 2013 | NOMADSS project debrief |  |
| 1 November 2013 | Release of final data set |  |

- Project Conditions:

  - Location

C-130 flight operations for the project will be coordinated with NOAA P-3 operations being flown in support of the SOAS ground based measurements.  These joint activities require the two aircraft to be collocated at a single airport.  The original deployment site of Nashville International Airport was deemed unsuitable for this requirement.  Both aircraft will be based at the Smyrna / Rutherford County Airport.  Work space for all NOMADSS instrument support groups will be made available in a hangar adjoining the aircraft ramp parking spaces for the two platforms.  The NOMADSS C-130  Data  Center will be off site at an alternate location.

  - Project Assumptions

- The NOMADSS C-130 deployment location is Smyrna, TN.

- The first day of NOMADSS science operations will be 1 June 2013.

- NOMADSS will be supported with a single flight crew.

- NOMADSS PI to serve as onboard Mission Scientist.

- NOMADSS individual flight durations will be between four and nine hours.

- The NOMADSS payload will require a total of eight weeks for installation including one week for local test flights.

- The aircraft flight plans call for clear sky conditions and will include flights in both high and low pollution conditions.

- The standard RAF display tools are sufficient for flight planning and real-time operations.

- Key payload components require extensive pre and post flight activity.  Activity on flight days will extend 3 or more hours beyond the actual flight durations.

- The standard EOL Data Center will be sufficient for NOMADSS operations; there is no need for a larger operations center.

- NOMADSS PI’s are responsible for the procurement of all instrument expendables, including calibration gases, cryogenics and other supplies.

- High speed internet access will be available at both the airport work space and the RAF Data Center to allow for communications between NOMADSS and SOAS scientists and the aircraft.

  - Project Constraints:

    - Payload

- Inlet line lengths are determined by C-130 infrastructure limitations.

- Instrument providers are responsible for sample line temperature control.

- All cabin based equipment must exhaust into standard sub-floor ducting to prevent possible contamination of downstream sensors.

- All compressed gas cylinders must be secured in approved infrastructure.  PI’s are responsible for plumbing gases from cylinders to sensors.

- Specialty inlets not currently available in the RAF inventory will be the responsibility of the instrument provider.

    - Operational

- Flight clearance problems may arise if flight tracks conflict with air traffic close to airports, restricted areas or active military operating areas (MOA’s).

- Flight routes will be adjusted by the C-130 pilots as necessary to avoid severe weather or other navigational hazards, and operations will be terminated if the safety of the aircraft is threatened.

- Flight operations will be constrained to U.S. controlled airspace.

- Flight operations will be limited to a minimum altitude of 1000 feet except for pre-planned low approaches into regional airports.

- Flight routes at altitudes below 2000 ft AGL will be adjusted by the C-130 pilots as necessary to avoid cities and large farms.

- Because of concurrent MPEX operations on the NSF/NCAR GV, the number of EOL staff in the field including necessary flight personnel will be limited increasing the chance of having to cancel a flight due to illness.

- The RAF data system technician, who will be onboard on all flights, cannot be responsible for the user equipment related tasks.

- Flight objectives requiring crew participation between the hours of 0000 and 0500 local time will require a switch in the diurnal duty cycle.

- Days off (hard-down days) will have to be scheduled at least 12 hours in advance.

- The following EOL/RAF crew duty limits will apply

| Flight Operations – Any 24-hour period | 10 flight hours |
| --- | --- |
| Flight Operations – Any consecutive 7 days | 40 flight hours; 60 duty hours |
| Flight Operations – Any 30-day period | 120 flight hours |
| Consecutive working days | 6 days |
| Maximum crew duty period | 14 consecutive hours |
| Minimum crew rest period | 12 consecutive hours |
| Consecutive maximum duty days | 2 days |
| Definition of Max. Duty Day | 10-14 hours |
| Night Duty | Show time earlier than 5 am LT Landing after midnight |
| Switch from Day to Night time operations | 36 hours |

4.4 Project Risks

| # | Risk Area | - Likeli-hood | - Risk Owner | - Project Impact-Mitigation Plan |
| --- | --- | --- | --- | --- |
| 1 | A number of hazardous materials are included in the NOMADSS research payload. | Low | RAF (Schanot) | Safety guidelines for the detection and mitigation of said hazards will be prepared by the instrument providers. All participants to be informed with these materials during the mandatory project safety briefing. |
| 2 | NOMADSS falls into an active weather season. Severe thunderstorm activity could pose a hazard for both aircraft and staff and interrupt science operations. | Med | RAF (Schanot) | Prior to the NOMADSS deployment, EOL will develop an evacuation plan for the C-130. EOL will monitor the development of severe weather in the region using normal publicly available warnings as well as discussions with the NOMADSS science team. If necessary, EOL may decide to ferry the aircraft to alternate airports for safety reasons. |
| 3 | Aircraft are subject to routine mechanical failures. Such an event could prevent flight operations for one or more days | Low | RAF (Schanot) | The aircraft is well maintained and travels with a special supply of key spare parts for rapid action. |
| 4 | Several of the key instruments in the payload are highly complex and require extensive preparation and continuous maintenance | Med | RAF (Schanot) Users (Instr PIs) | Upload schedules will be set and enforced to allow adequate time to integrate and test all payload components. Maintenance days will be scheduled during the deployment to provide access on non-flight days. PI’s to establish list of mission sensitive systems for flight decisions |
| 5 | Targeted research area includes high traffic zones, restricted areas and MOAs. Pre-flight tracks will be adjusted by the pilots as needed | Med | RAF (Pilots) Users (Mission Scientist) | Pattern specific science objectives could be affected. Planned flight tracks will be adjusted by the pilots at their discretion to avoid flight hazards, cities and farms. |
| 6 | C-130 to undergo a major structural inspection prior to the scheduled deployment interval | Low | RAF (Stith) | Delays in the return of the C-130 to full service would result in commensurate delays in all project activities. Provisions are in place to defer some inspection activities to meet our obligations |
| 7 | Extensive infrastructure upgrades are required to support the research payload. DFS delays could impact the upload schedule | Med | RAF (Schanot) DFS (Ranson) | Payload to be finalized as scheduled with early submittal of fabrication tasks to DFS |
| 8 | Close formation flight tracks with the NOAA P-3 for sensor intercomparisons | Low | RAF (Pilots) | Pilots from both NCAR and NOAA will meet prior to scheduling this mission to coordinate in flight procedures for this activity. |

4.5 Project Issues

| # | Date | Priority | Owner | Description | Status & Resolution |
| --- | --- | --- | --- | --- | --- |
| 1 | 12/26/12 | Med | Schanot | Finalize payload | Awaiting funding decision on SMPS staffing and detailed information on potential addition of User SO2 analyzer. |
| 2 |  | Med |  |  |  |
| 3 |  | Med |  |  |  |
| 4 |  | Med |  |  |  |

- Project References

| Document/Reference | Description / hyperlink |
| --- | --- |
| NOMADSS Approval Notice | Sent to (available from Baeuerle, Cheeseman or Albright) |
| Project Summary – NOMADSS | NCAR/EOL –Spring 2012 OFAP MEETING |
| Request for LAOF Support – SOAS / NAAMEX / TROPHONO | NCAR/EOL – Spring 2012 OFAP MEETING |
| Feasibility Analysis – SOAS / NAAMEX / TROPHONO | NCAR/EOL –Spring 2012 OFAP MEETING |
| NOMADSS Cost Estimate | NCAR/EOL –Spring 2012 OFAP MEETING |

Priority Criteria

1 − High-priority/critical-path issue; requires immediate follow-up and resolution

2 − Medium-priority issue; requires follow-up before completion of next project milestone

3 − Low-priority issue; to be resolved prior to project completion

4 − Closed issue